## Control Registry
UCCA Canonical Control Registry v2.0
38 controls across 12 domains ¦ UCCA-Control-Object Architecture
Last updated: 2026-03-04
Control ID | Domain | Description | SOC 2 Mapping | NIST Mapping | Status | Evidence Location | Last Reviewed | Gap Notes | Priority
UCCA-AC-001 | Access Governance | Logical Access Control: Restrict system access to authorised users via Cloudflare IAM and GitHub PATs with fine-grained scoping. | CC6.1, CC6.2 | AC-2, AC-3 | P | Cloudflare IAM, GitHub PATs, macOS Keychain | 2026-03-03 | Secondary admin gap. Single account risk. | Critical
UCCA-AC-002 | Access Governance | Privileged Account Segregation: Separate admin and operational accounts. No shared credentials. Least privilege enforced. | CC6.1, CC6.3 | AC-6 | N | -- | -- | Only one admin account exists (Tim). No segregation possible yet. | Critical
UCCA-AC-003 | Access Governance | Provisioning and Deprovisioning: Documented process for granting and revoking access when personnel join or leave. | CC6.3 | AC-2 | N | -- | -- | No formal onboarding/offboarding checklist. | High
UCCA-AC-004 | Access Governance | Quarterly Access Review: Review all user access quarterly with dated sign-off evidence. | CC6.1 | AC-2 | N | -- | -- | No review cadence established. | High
UCCA-AU-001 | Audit and Evidence | Centralised Logging: All system events logged to a central store with retention policy. | CC7.1 | AU-3, AU-6 | P | Cloudflare analytics, ops.ucca.online | 2026-03-03 | Logs exist but no formal retention policy. | Medium
UCCA-AU-002 | Audit and Evidence | Log Review Cadence: Logs reviewed on a defined schedule with sign-off evidence. | CC7.1, CC7.2 | AU-6 | N | -- | -- | No review schedule. No sign-off trail. | Medium
UCCA-AU-003 | Audit and Evidence | Time Synchronisation: All systems synchronised to authoritative time source. | CC7.1 | AU-8 | Y | Cloudflare edge (NTP synced) | 2026-03-03 | Cloudflare Workers use edge time. No local clock drift. | --
UCCA-CM-001 | Configuration and Change | Infrastructure as Code Baseline: All infrastructure defined in version-controlled IaC with reproducible state. | CC8.1 | CM-2 | Y | Terraform state, 120+ resources | 2026-03-03 | Full IaC via Terraform. Reproducible. | --
UCCA-CM-002 | Configuration and Change | Version-Controlled Change Management: All changes via git with branch, review, merge workflow. | CC8.1 | CM-3 | Y | Git history, feature branches | 2026-03-03 | Needs formal change management policy document. | Medium
UCCA-CM-003 | Configuration and Change | Deployment Controls: Deployments follow defined process with rollback capability. | CC8.1 | CM-3 | P | Terraform plan/apply, Wrangler deploy | 2026-03-03 | Process exists. No formal deployment policy. | Medium
UCCA-IA-001 | Identity and Auth | MFA Enforcement: Multi-factor authentication required on all administrative accounts. | CC6.1 | IA-2 | P | Cloudflare (MFA), GitHub (MFA) | 2026-03-03 | MFA on primary services. Not documented as policy. | High
UCCA-IA-002 | Identity and Auth | Secrets and Key Management: API keys, tokens, and credentials stored securely with rotation schedule. | CC6.2 | IA-5 | P | macOS Keychain, GitHub PATs | 2026-03-03 | PAT expires Mar 2026. No rotation calendar. | High
UCCA-IA-003 | Identity and Auth | Credential Lifecycle: Defined process for credential creation, rotation, and revocation. | CC6.2, CC6.3 | IA-5 | N | -- | -- | No documented lifecycle process. | High
UCCA-IR-001 | Incident Response | Incident Response Plan: Documented IR plan with severity levels, escalation paths, and notification procedures. | CC7.3 | IR-1 | N | -- | -- | No formal IR plan exists. | High
UCCA-IR-002 | Incident Response | Incident Tracking: All incidents logged with timeline, actions taken, and resolution. | CC7.2, CC7.3 | IR-5, IR-6 | N | -- | -- | No incident log maintained. | Medium
UCCA-IR-003 | Incident Response | Annual Tabletop Exercise: Simulated incident response exercise conducted annually with documented results. | CC7.3 | IR-2 | N | -- | -- | No tabletop exercise conducted. | High
UCCA-RA-001 | Risk and Threat | Annual Risk Assessment: Formal risk assessment with likelihood/impact scoring, reviewed annually. | CC3.1 | RA-3 | P | Governance workbook - Risk Register | 2026-03-04 | Risk register created. Needs formal annual review cycle. | Critical
UCCA-RA-002 | Risk and Threat | Risk Register: Living risk register with scored risks, mitigations, owners, and review dates. | CC3.2 | RA-3 | Y | Governance workbook - Risk Register | 2026-03-04 | 10 risks scored. Quarterly review TBD. | --
UCCA-RA-003 | Risk and Threat | Threat Modelling Review: Periodic review of threat landscape relevant to UCCA platform and clients. | CC3.1 | RA-5 | N | -- | -- | No formal threat model. | Medium
UCCA-CP-001 | Continuity and Recovery | Business Continuity Plan: Documented BCP covering critical systems, recovery scenarios, and communication. | CC7.5 | CP-2 | P | BCP v2.0 in knowledge-site | 2026-03-03 | BCP drafted. Needs formal sign-off. | High
UCCA-CP-002 | Continuity and Recovery | RTO/RPO Definition: Recovery Time and Recovery Point Objectives defined for all critical systems. | CC7.5 | CP-2 | N | -- | -- | Not formally defined. Draft values in BCP. | High
UCCA-CP-003 | Continuity and Recovery | Backup and Restore Testing: Annual backup restoration test with documented results. | CC7.5 | CP-9 | N | -- | -- | No restoration test conducted. D1 has auto backups. | High
UCCA-SC-001 | Boundary and Protection | Encryption Enforcement: All data encrypted in transit (TLS) and at rest. | CC6.7 | SC-8, SC-28 | Y | Cloudflare TLS 1.3, HSTS, D1 encryption | 2026-03-03 | Grade A TLS across all properties. | --
UCCA-SC-002 | Boundary and Protection | Network Boundary Definition: Network boundaries documented with ingress/egress controls. | CC6.6 | SC-7 | Y | Cloudflare WAF, edge network | 2026-03-03 | All traffic through Cloudflare edge. | --
UCCA-SC-003 | Boundary and Protection | WAF and DDoS Controls: Web application firewall and DDoS mitigation active on all public endpoints. | CC6.6 | SC-5, SC-7 | Y | Cloudflare WAF, rate limiting, DDoS | 2026-03-03 | Active on all domains. | --
UCCA-SI-001 | Integrity and Monitoring | Vulnerability Scanning: Regular vulnerability scanning of public-facing systems. | CC7.1 | SI-2 | N | -- | -- | No scanning tool configured. | Medium
UCCA-SI-002 | Integrity and Monitoring | Patch Management: Defined process for applying security patches to dependencies. | CC7.1 | SI-2 | P | npm audit, dependabot alerts | -- | Reactive not proactive. No policy. | Medium
UCCA-SI-003 | Integrity and Monitoring | Dependency Scanning: Automated scanning of third-party dependencies for known vulnerabilities. | CC7.1 | SI-2 | P | GitHub Dependabot | 2026-03-03 | Enabled but no review process. | Medium
UCCA-SR-001 | Supply Chain | Vendor Inventory: Complete inventory of all vendors with data sensitivity and criticality classification. | CC9.2 | SA-9 | Y | Governance workbook - Vendor Register | 2026-03-04 | 7 vendors registered. | --
UCCA-SR-002 | Supply Chain | Vendor Risk Assessment: Risk assessment performed on all critical vendors. | CC9.2 | SA-9 | N | -- | -- | No vendor SOC 2/ISO reports on file. | High
UCCA-SR-003 | Supply Chain | Critical Vendor Review: Annual review of critical vendor security posture. | CC9.2 | SA-9 | N | -- | -- | No review conducted. | High
UCCA-GV-001 | Governance | Security Policy and Ownership: Board-approved security policy with designated owner and annual review cycle. | CC1.1 | PL-1 | N | -- | -- | No formal security policy document. | High
UCCA-GV-002 | Governance | Control Review Cadence: All controls reviewed on defined cadence with evidence of review. | CC4.1 | CA-2 | N | -- | -- | No review cadence established. | High
UCCA-GV-003 | Governance | Evidence Retention Governance: Policy defining evidence types, retention periods, and storage locations. | CC4.1 | AU-11 | N | -- | -- | No evidence retention policy. | Medium
UCCA-DV-001 | UCCA Moat | Deterministic Verification Enforcement: All verification operations use deterministic, non-AI logic with reproducible results. | -- | -- | Y | UCCA Engine architecture | 2026-03-03 | Core architectural principle. Engine by design. | --
UCCA-EF-001 | UCCA Moat | Immutable Evidence Fingerprinting: All verification evidence is hashed and immutable once generated. | -- | -- | P | Evidence chain design | 2026-03-03 | Architecture supports it. Not yet in production. | Medium
UCCA-AP-001 | UCCA Moat | Regulatory Source Provenance: All authority data traces to its regulatory source with audit trail. | -- | -- | Y | TGA API mirror, X-UCCA provenance headers | 2026-03-03 | Full provenance chain from TGA to D1. | --
UCCA-CI-001 | UCCA Moat | Capability Object Lifecycle Integrity: Capability objects maintain integrity through create, verify, update, archive lifecycle. | -- | -- | P | Engine design, schema v4 | 2026-03-03 | Schema supports it. Lifecycle not yet enforced in code. | Medium

## Posture Dashboard
Control Family Posture Dashboard
Executive summary by domain
Last updated: 2026-03-04
Domain | Controls | Green (Y) | Partial (P) | Gap (N) | Posture | Top Priority | Owner
Access Governance | 4 | 0 | 1 | 3 | Gap | UCCA-AC-001 - Logical Access Control | Tim
Audit and Evidence | 3 | 1 | 1 | 1 | Partial | -- | Tim
Configuration and Change | 3 | 2 | 1 | 0 | Strong | -- | Tim
Identity and Auth | 3 | 0 | 2 | 1 | Gap | UCCA-IA-001 - MFA Enforcement | Tim
Incident Response | 3 | 0 | 0 | 3 | Gap | UCCA-IR-001 - Incident Response Plan | Tim
Risk and Threat | 3 | 1 | 1 | 1 | Partial | UCCA-RA-001 - Annual Risk Assessment | Tim
Continuity and Recovery | 3 | 0 | 1 | 2 | Gap | UCCA-CP-001 - Business Continuity Plan | Tim
Boundary and Protection | 3 | 3 | 0 | 0 | Strong | -- | Tim
Integrity and Monitoring | 3 | 0 | 2 | 1 | Gap | -- | Tim
Supply Chain | 3 | 1 | 0 | 2 | Partial | UCCA-SR-002 - Vendor Risk Assessment | Tim
Governance | 3 | 0 | 0 | 3 | Gap | UCCA-GV-001 - Security Policy and Ownership | Tim
UCCA Moat | 4 | 2 | 2 | 0 | Partial | -- | Tim
TOTAL | 38 | 10 | 11 | 17

## Risk Register
Risk Register
Likelihood x Impact (1-5) ¦ Score = L x I
Last updated: 2026-03-04
Risk ID | Description | Domain | Likelihood | Impact | Score | Mitigation | Owner | Status | Review Date
R-001 | Single admin account -- bus factor of 1 | Access Governance | 4 | 5 |  | Create secondary admin on CF/GH/domain. Add Jimmy. | Tim | Open | 2026-03-04
R-002 | No formal incident response plan | Incident Response | 3 | 4 |  | Draft IR plan with severity levels and escalation. | Tim | Open | 2026-03-04
R-003 | Cloudflare single-vendor dependency | Supply Chain | 2 | 5 |  | Document DR scenario. Evaluate DNS failover options. | Tim | Open | 2026-03-04
R-004 | No quarterly access review cadence | Access Governance | 3 | 3 |  | Establish quarterly calendar with sign-off template. | Tim | Open | 2026-03-04
R-005 | MacBook as sole ingestion gateway | Continuity | 3 | 3 |  | Document recovery. Evaluate Worker-based ingestion. | Tim | Open | 2026-03-04
R-006 | GitHub PAT expires Mar 2026 | Identity and Auth | 4 | 4 |  | Rotate immediately. Document rotation procedure. | Tim | Open | 2026-03-04
R-007 | No backup restoration test evidence | Continuity | 2 | 4 |  | Schedule D1 restoration test. Document results. | Tim | Open | 2026-03-04
R-008 | TGA API dependency -- no SLA | Supply Chain | 3 | 3 |  | Local mirror exists (493K rows). Document refresh cadence. | Tim | Mitigated | 2026-03-04
R-009 | No vendor SOC 2/ISO reports on file | Supply Chain | 2 | 3 |  | Request Cloudflare SOC 2. Review GitHub security. | Tim | Open | 2026-03-04
R-010 | Knowledge concentration in Tim | Governance | 3 | 5 |  | Knowledge-site docs. ARM v1.0. World Container Spec. | Tim | In Progress | 2026-03-04
R-011 | No formal security policy document | Governance | 2 | 4 |  | Draft security policy. Obtain sign-off. | Tim | Open | 2026-03-04
R-012 | Platform/world code boundary undefined | Configuration | 3 | 3 |  | World Container Spec v1.0 drafted. Migration planned. | Tim | In Progress | 2026-03-04

## Vendor Register
Vendor Register
Critical vendor inventory and risk classification
Last updated: 2026-03-04
Vendor | Service | Sensitivity | Critical? | SOC 2? | ISO 27001? | FedRAMP? | Reviewed | Risk Notes
Cloudflare | CDN, WAF, DNS, D1, Workers, R2, Zero Trust | High | Yes | Yes (request) | Yes | FedRAMP Moderate | -- | Primary infra. Single-vendor risk R-003
GitHub | Source code, version control, CI | High | Yes | Yes (request) | -- | -- | -- | All repos. Fine-grained PATs
Anthropic | Claude AI (strategy), Claude Code (implementation) | Medium | Yes | Unknown | -- | -- | -- | Dev collaboration only. No production data
training.gov.au | Authority data source (TGA REST API) | Low | Yes | N/A (govt) | N/A | N/A | -- | Public API. Full mirror in D1 (493K rows)
Apple macOS | Development workstation | Medium | No | -- | -- | -- | -- | FileVault enabled. Sole ingestion gateway
Namecheap | Domain registration | Low | Yes | Unknown | -- | -- | -- | ucca.online, rtopacks.com.au, ucca.asia, etc
Mercury Bank | Corporate banking, AWS credits program | Low | No | -- | -- | -- | -- | Banking and startup perks
Google | Drive (backup), Workspace | Low | No | -- | -- | -- | -- | Document backup. Not production

## Evidence Log
Evidence Log
Timestamped proof -- auditors sample this sheet
Last updated: 2026-03-04
Control ID | Evidence Type | Location | Date | Reviewer | Review Date | Notes
UCCA-CM-001 | Terraform state | Cloudflare / terraform.tfstate | 2026-03-03 | Tim | -- | 120+ resources under IaC
UCCA-CM-002 | Git commit history | github.com/uccaonline/ucca-engine | 2026-03-03 | Tim | -- | Full history with feature branches
UCCA-CM-001 | Infrastructure baseline | Terraform config in ucca-engine | 2026-03-03 | Tim | -- | Reproducible. Version controlled
UCCA-AC-001 | PAT configuration | GitHub Settings > Fine-grained PATs | 2026-03-03 | Tim | -- | ucca-engine-push, expires Mar 2026
UCCA-SC-001 | TLS configuration | Cloudflare SSL/TLS settings | 2026-03-03 | Tim | -- | Grade A across all 10 domains
UCCA-SC-003 | WAF configuration | Cloudflare WAF dashboard | 2026-03-03 | Tim | -- | WAF active, DDoS mitigation, rate limiting
UCCA-SI-003 | Dependency scanning | GitHub Dependabot alerts | 2026-03-03 | Tim | -- | Enabled on all repositories
UCCA-AU-001 | Monitoring dashboard | ops.ucca.online | 2026-03-03 | Tim | -- | Live monitoring with health checks
UCCA-CP-001 | Business continuity plan | ucca-docs /governance/bcp-v2 | 2026-03-03 | Tim | -- | BCP v2.0 drafted. Needs sign-off
UCCA-RA-002 | Risk register | Governance workbook v2.0 | 2026-03-04 | Tim | -- | 12 risks scored across 7 domains
UCCA-SR-001 | Vendor inventory | Governance workbook v2.0 | 2026-03-04 | Tim | -- | 8 vendors classified
UCCA-AP-001 | Data provenance chain | D1 rtopacks-db + TGA API | 2026-03-04 | Tim | -- | 493,484 rows with source traceability
UCCA-DV-001 | Engine architecture | ucca-engine repo + ARM v1.0 | 2026-03-03 | Tim | -- | Deterministic by design. Non-AI verification